## All Risks
| SEG Risk Management Plan | Version 1.0, 28 November 2023
[10 empty] | 0=it will not happen, 5=certainty. | [5 empty] | Coding: 0 to 5, where 0=ok, and 5=bad. Note that 0 (not 1) is so ok, that nothing else matters anymore.
| Notes | [8 empty] | 0=it will not affect us, 5=pain | [5 empty] | A. Likelihood, ranging from 0=absolutely impossible to 5=absolutely certain.
| 1. All Threats to achievement of SEG Objectives transcribed from 018b, SEG Threats | [8 empty] | 0=no choice, 5=up to us! | [5 empty] | B. Impact if it happens. From 0=no effect whatsoever, to 5=catastrophic effect.
| 2. Not all Threats fully assessed for risk and mitigated yet | [8 empty] | 0=we do not care, 5=our focus! | [5 empty] | C. Options we have. From 0=we cannot do anything, to 5=it is fully in our hands.
| 3. Priority to date has been on Assurance Risks (see next Tab) | [8 empty] | 0=dealt with, safe, 5=wake up! | [5 empty] | D. Focus. From 0= we do not care at all, to 5=deepest concern, full in focus.
E. Unmitigated risk = L x I
0 |  | A. Likelihood | B. Impact | C. Options available | D. Focus, priority | E. Unmitigated risk | F. target risk, acceptance | Gap | Actions | Position | Mitigated L | Mitigated I | Mitigated Risk at 21/11/23 | Mitigateed Gap at 21/11/23 | A*B. Raw risk | A*B*C*D. Priority | A*B*C*D*E. Alarming | Comment
1 |  | A: GOVERNANCE AND MANAGEMENT OF SEG
2 |  | Governance
3 | Slow responses to major and/or urgent issues | 2 | 2 | 2 | 2 | 1 | 9 | -5 | [6 empty] | 4 | 16 | 16
4 | Inability to handle multiple issues simultaneously | 2 | 3 | 3 | 3 | 2 | 4 | 2 | [6 empty] | 6 | 54 | 108
5 | Lack of crisis management plan | 4 | 2 | 3 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 48 | 48
6 |  | Management
7 | Insufficient internal auditing | 1 | 2 | 3 | 1 | 1 | 16 | -14 | [6 empty] | 2 | 6 | 6
8 | Insufficient management reviews | 1 | 2 | 3 | 1 | 2 | 16 | -14 | [6 empty] | 2 | 6 | 12
9 | Insufficient risk management | 1 | 2 | 3 | 1 | 2 | 16 | -14 | [6 empty] | 2 | 6 | 12
10 |  | Business model
11 | Over-reliance on few or fragile or inconsistent income sources | 1 | 1 | 1 | 0 | 1 | 25 | -24 | [6 empty] | 1 | 0 | 0 | Our choice!
12 | Limited viability of business model (e.g. competition with lower cost/more ethical/more niche, niche/more broad) (a risk and a purpose) | 1 | 1 | 1 | 0 | 1 | 25 | -24 | [6 empty] | 1 | 0 | 0 | When done, we are done.
13 | Erosion of market differentiation | 1 | 1 | 1 | 0 | 1 | 25 | -24 | [6 empty] | 1 | 0 | 0
14 | Wariness of collaboration with ‘competition’ and/or with corporate sector | 3 | 2 | 3 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 18 | 54 | Getting bored by our own success
15 | Not listening sufficiently to customers or members | 1 | 2 | 3 | 4 | 1 | 1 | 1 | [6 empty] | 2 | 24 | 24
16 |  | Change management
17 | Limited perception of standard system in a ‘post-labelling context’ | 1 | 3 | 3 | 1 | 4 | 16 | -13 | [6 empty] | 3 | 9 | 36
18 |  | Human resources
19 | Loss of key staff, and/or institutional memory | 5 | 3 | 3 | 3 | 2 | 4 | 11 | [6 empty] | 15 | 135 | 270 | Aware, remedies discussed
20 | Insufficient ongoing training | 1 | 3 | 2 | 2 | 0 | 9 | -6 | [6 empty] | 3 | 12 | 0
21 | Insufficient clarity in responsibilities (including for risk management) | 1 | 2 | 2 | 1 | 1 | 16 | -14 | [6 empty] | 2 | 4 | 4
22 |  | Information and learning
23 | Lack of timely, consistent system-wide data on which to base decisions | 5 | 2 | 0 | 1 | 1 | 16 | -6 | [6 empty] | 10 | 0 | 0 | Eel is complex, always.
24 | Key Performance Indicators (including for auditors and CABs) inadequate to assess impact and highlight problems | 1 | 2 | 1 | 0 | 1 | 25 | -23 | [6 empty] | 2 | 0 | 0 | Informal outdoes formal
25 | Lack of data on impacts | 1 | 1 | 0 | 3 | 3 | 4 | -3 | [6 empty] | 1 | 0 | 0 | We accommodate for no data
26 | Insufficient ‘learning and change’ component of M&E system | 0 | 4 | 3 | 3 | 3 | 4 | -4 | [6 empty] | 0 | 0 | 0
27 | Lack of access to necessary certificate holder data | 5 | 1 | 1 | 2 | 2 | 9 | -4 | [6 empty] | 5 | 10 | 20 | a certainty
28 | Insufficient professional analysis of successes and failures | 1 | 3 | 3 | 2 | 1 | 9 | -6 | [6 empty] | 3 | 18 | 18
29 |  | Communication
30 | Producer needs not sufficiently heard | 1 | 3 | 2 | 2 | 2 | 9 | -6 | [6 empty] | 3 | 12 | 24
31 | Lack of market awareness of SEG system and associated benefits | 1 | 4 | 2 | 2 | 2 | 9 | -5 | [6 empty] | 4 | 16 | 32
32 | Impacts fall short of stated expectations or claims | 1 | 4 | 2 | 2 | 2 | 9 | -5 | [6 empty] | 4 | 16 | 32
33 | Media, partners and peers insufficiently understanding the approach, context or Theory of Change | 3 | 1 | 1 | 1 | 2 | 16 | -13 | [6 empty] | 3 | 3 | 6
34 | Customer confusion between different standards and logos | 2 | 1 | 1 | 1 | 2 | 16 | -14 | [6 empty] | 2 | 2 | 4 | B2B approach avoids the consumer.
35 | False perceptions of what certification or logo or label means | 2 | 1 | 4 | 4 | 0 | 1 | 1 | [6 empty] | 2 | 32 | 0 | We dealt with the risk!
36 | Traceability/mass balance not sufficiently communicated to stakeholders | 1 | 3 | 3 | 2 | 0 | 9 | -6 | [6 empty] | 3 | 18 | 0 | Aware and dealing with
37 |  | B: POLITICAL AND CULTURAL
38 | European Commission and key member states cease to support, or restrict sustainable eel trade | 1 | 4 | 2 | 0 | 1 | 25 | -21 | [6 empty] | 4 | 0 | 0 | Not our responsibility
39 | Insufficient interest from European Commission | 1 | 4 | 2 | 0 | 1 | 25 | -21 | [6 empty] | 4 | 0 | 0
40 | Opposition to sustainable eel trade by NGOs in key countries | 1 | 4 | 2 | 2 | 0 | 9 | -5 | [6 empty] | 4 | 16 | 0 | We just dealt with it!
41 | Slow or insufficient implementation of Eel Management Plans | 5 | 4 | 1 | 4 | 0 | 1 | 19 | [6 empty] | 20 | 80 | 0 | A certainty we deal with
42 | Slow or ineffective implementation of Water Framework Directive | 2 | 4 | 0 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 0 | 0
43 | Illegal trade weakens and discredits sustainable eel trade | 4 | 3 | 1 | 4 | 1 | 1 | 11 | [6 empty] | 12 | 48 | 48 | A certainty
44 | Divergence of scientific, conservation and commercial viewpoints | 1 | 3 | 1 | 2 | 0 | 9 | -6 | [6 empty] | 3 | 6 | 0 | Internal or external?
45 | Travel and on-site safety issues for auditors | 2 | 4 | 1 | 2 | 0 | 9 | -1 | [6 empty] | 8 | 16 | 0 | We deal with that!
46 | Diversity of location-specific and product-specific issues for producers and workers | 4 | 3 | 1 | 2 | 0 | 9 | 3 | [6 empty] | 12 | 24 | 0 | Evidently, and we deal with it
47 | Donor/market change leads to less support, or interest from consumers | 3 | 3 | 0 | 1 | 4 | 16 | -7 | [6 empty] | 9 | 0 | 0 | But what to do?
48 | Shift in political, customer or NGO focus to other environmental and social justice issues | 1 | 4 | 1 | 2 | 0 | 9 | -5 | [6 empty] | 4 | 8 | 0 | We have just created lots of attention
49 | Small number of corporations achieve dominance through market share and exercise control | 2 | 2 | 0 | 1 | 2 | 16 | -12 | [6 empty] | 4 | 0 | 0 | Accepted as unavoidable
50 | Producer representatives do not know enough of, or inadequately represent producers' issues | 1 | 4 | 1 | 1 | 4 | 16 | -12 | [6 empty] | 4 | 4 | 16
51 | Increasing average age of producers | 5 | 4 | 0 | 1 | 5 | 16 | 4 | [6 empty] | 20 | 0 | 0 | Happens only where gov decides so. That is not risk.
52 | Low or high commodity prices affect marginal value of certification | 1 | 3 | 0 | 1 | 4 | 16 | -13 | [6 empty] | 3 | 0 | 0 | Prices high, as always
53 |  | C: TECHNICAL
54 | Cyber hacking, loss of data, loss of confidentiality | 3 | 3 | 1 | 1 | 4 | 16 | -7 | [6 empty] | 9 | 9 | 36 | No remedy available.
55 |  | D: ASSURANCE SYSTEM
56 |  | Auditor performance, competence and skills inadequate
57 | Insufficient approved CABs | 4 | 4 | 2 | 4 | 16 | 4 | 12 | 1. Find and appoint additional CAB. 2. SEG to act as CB as a contingency. | 1. New CAB just appointed, to seek another. 2. SEG is contingency CB | 3 | 3 | 9 | 5 | 16 | 128 | 2048 | And we deal with it.
58 | Auditors too lenient (Including NCs not raised, ‘low graded’ and closed too readily) including through overfamiliarity. | 2 | 3 | 2 | 2 | 6 | 4 | 2 | 1. Apply training for all new auditors. 2. Apply QA of 10% of audits | 1. All new auditors have training. 2. So far 100% of audits have been checked | 1 | 2 | 2 | -2 | 6 | 24 | 144 | All the same
59 | Auditor competence insufficient | 2 | 3 | 2 | 2 | 6 | 4 | 2 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 6 | 24 | 144
60 | Inadequate auditor training | 3 | 3 | 2 | 2 | 9 | 4 | 5 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 9 | 36 | 324
61 | Auditor qualifications, skills and experience insufficient | 2 | 4 | 2 | 2 | 8 | 4 | 4 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 8 | 32 | 256
62 | Audits too brief | 3 | 3 | 2 | 2 | 9 | 4 | 5 | 1. Guidance in auditor training | 1. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 9 | 36 | 324
63 | Auditors given insufficient direction with lack of consistency of findings | 2 | 4 | 2 | 2 | 8 | 4 | 4 | [6 empty] | 8 | 32 | 256
64 | Insufficient local stakeholder engagement by CABs | 2 | 4 | 2 | 2 | 8 | 4 | 4 | [6 empty] | 8 | 32 | 256
65 |  | Standard and assurance system design, insufficiently facilitates certification integrity
66 |  | Standard system design
67 | Important issues hard to detect | 4 | 4 | 1 | 1 | 4 | 4 | 12 | 1. Update Standard to include Risk Assessment, with Guidance. 2. Include in Auditor training | 1. Standard updated. 2. Included in training package | 2 | 2 | 4 | 0 | 16 | 16 | 64
68 | Indicators too open to interpretation (NB allowing CABs to interpret leniently/inconsistently) | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36 | All realistic, and we dealt with it.
69 | Standard interpretations insufficiently objective | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36
70 | Auditors over-dependent on information provided by certificate holders or applicants (CHs) | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36 | Never change a winning culture
71 | Assurance system unable to adequately respond to significant growth in number of CHs | 2 | 3 | 1 | 1 | 4 | 4 | 2 | [6 empty] | 6 | 6 | 24 | The A culture should not strangle the existing creativity.
72 |  | Assurance system design
73 | Insufficient unannounced audits | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Build resource into CAB agreeement | 1. In CAB agreement | 2 | 3 | 6 | 2 | 12 | 24 | 72
74 | Insufficient sample sizes within audits | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
75 | Requiring CABs to make frequent communications with CHs about changes to the standard | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
76 | Fraud and corruption by CHs | 4 | 5 | 2 | 1 | 3 | 4 | 16 | 1. Training to auditors and CAB what to look for 2. Sufficient sanctions and control measures in Assurance System | 1. Training package updated - particularly by Lead Auditor on this topic. 2. Assurance has strong sanctions, eg. suspension | 3 | 3 | 9 | 5 | 20 | 40 | 120
77 | ‘Empty certificates’, i.e. those granted to CHs not actively engaged in harvest, production or trade | 2 | 2 | 2 | 1 | 3 | 4 | 0 | [6 empty] | 4 | 8 | 24
78 | Poor follow-up to low assurance quality | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Training for auditors to reduce low assurance quality. 2. Requirement for CAB to follow up | 1. Training package in place and refreshers due Dec 2023 2. CAB agreement in place from 7-11-23 | 2 | 2 | 4 | 0 | 12 | 24 | 72
79 |  | Oversight system design
80 | Oversight too lenient (Including NCs not raised, ‘low graded’ and closed too readily) including through overfamiliarity. | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
81 | Oversight personnel competence, training, qualifications, skills or experience insufficient | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
82 | Important issues hard to detect | 4 | 4 | 2 | 1 | 3 | 4 | 12 | 1. Training for auditors to reduce low assurance quality. 2. Requirement for CAB to follow up | 1. Training package in place and refreshers due Dec 2023 2. CAB agreement in place from 7-11-23 | 2 | 2 | 4 | 0 | 16 | 32 | 96
83 | Oversight over-dependent on information provided by CABs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
84 | CAB approval based more on conformance than performance | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
85 | Oversight system unable to adequately respond to significant growth in number of CABs | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
86 | CAB non-conformity (NC) implications too lenient | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Build performance measurew and sanctions into CAB agreement | 1. Performance measures and sanctions built into CAB agreement | 2 | 3 | 6 | 2 | 12 | 24 | 72
87 | Insufficient sample sizes within oversight | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
88 | Insufficient witness and compliance audits | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
89 | Fraud and corruption by CABs | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
90 |  | Standard-assurance interaction
91 | Inadequate risk basis to certification or CAB approval | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Update Standard to include Risk Assessment, with Guidance. 2. Include in Auditor training | 1. Standard updated. 2. Included in training package | 2 | 3 | 6 | 2 | 12 | 24 | 72
92 | Over-reliance on audits | 3 | 2 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
93 | Mixed messages and guidance on standard interpretation to CABs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
94 |  | Difficulty in making changes
95 |  | Insufficient impartiality
96 | CAB impartiality compromised by business benefits from ‘good CH relationships’ | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
97 | Auditor impartiality compromised by benefits from ‘good CH relationships’ | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Require oversight by CAB 2. Update standard and add risk assessment | 1. Oversight in CAB agreement 2. Standard updated with risk assessment and guidance | 2 | 3 | 6 | 2 | 12 | 24 | 72
98 | CABs become “Too big to fail” | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
99 |  | Quality not incentivised
100 | CABs compete more on cost than on quality; CABs incentivised to maintain and increase income from CHs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
101 | Insufficient connection between assurance and market benefit | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
102 |  | Inconsistent CAB approval quality
103 | CAB approval assessments not frequent enough | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
104 | CAB approval inconsistent (CAB approval body not providing a level playing field for CABs) and/or too lenient | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
105 | Insufficient competition between CAB approval bodies or insufficient control over monopolistic behaviour | 1 | 3 | 2 | 1 | 3 | 4 | -1 | [6 empty] | 3 | 6 | 18
106 | CAB approval body staff with insufficient availability and technical understanding | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Undertake succession planning and/or sharing of expertise | 1. To be done | 3 | 4 | 12 | 8 | 12 | 24 | 72
107 | Insufficient calibration between CABs | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
108 |  | Inadequate 2-way communication and transparency
109 |  | Communications
110 | Insufficient public interest in eel conservation and sustainable eel trade | 4 | 4 | 1 | 1 | 0 | 4 | 12 | [6 empty] | 16 | 16 | 0
111 |  | E: MARKET CONDITIONS
112 | Supply of certified products greatly exceeding demand | 1 | 1 | 0 | 2 | 2 | 4 | -3 | [6 empty] | 1 | 0 | 0 | Self-correcting
113 |  | F: REPUTATION AND INFLUENCE
114 | Standard not accepted and criticised by major stakeholder | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0 | That is the point of iseal
115 | SEG fails to achieve full ISEAL Code-compliant membership | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0
116 | Reduced trust associated with improper certification, or certificate holder conviction i.e. reporting is largely accurate | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0 | 5 / 0
117 | Fraud, or corruption by certificate holders or CABs | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0
118 | Weaknesses in certification and assurance systems related to [client] covert issues. | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0
119 | Guilt by association with suppliers/retailers with other sustainabilty and responsibility issues | 5 | 3 | 0 | 3 | 0 | 4 | 11 | [6 empty] | 15 | 0 | 0
120 | Shift of trade to less discerning markets | 1 | 3 | 0 | 3 | 0 | 4 | -1 | [6 empty] | 3 | 0 | 0 | cultures change slowly, poaching
121 |  | G: THREATS AT LOCAL LEVEL
122 |  | Local inability to raise performance to necessary level for certification
123 | High investment costs for sustainable management | 4 | 3 | 1 | 2 | 1 | 4 | 8 | [6 empty] | 12 | 24 | 24
124 | Limited access to technology or communications | 4 | 3 | 1 | 2 | 1 | 4 | 8 | [6 empty] | 12 | 24 | 24
125 | Poor local understanding or awareness of requirements | 4 | 3 | 1 | 2 | 1 | 4 | 8 | [6 empty] | 12 | 24 | 24
126 | Restrictive local business models or regulations | 4 | 3 | 1 | 2 | 1 | 4 | 8 | [6 empty] | 12 | 24 | 24
127 |  | Other external factors |  |  |  |  | 4
128 | Harvest fragility through over-fishing, disease, Gulf Stream change, extreme weather events, etc. | 5 | 5 | 0 | 2 | 2 | 4 | 21 | [6 empty] | 25 | 0 | 0 | Happens!
129 | Terrorism, military activity, land tenure issues, migration, political stability | 5 | 5 | 0 | 2 | 2 | 4 | 21 | [6 empty] | 25 | 0 | 0 | Above our head
130 | Unsustainable neighbouring land-use practices, and other external sustainability threats | 5 | 5 | 0 | 2 | 2 | 4 | 21 | [6 empty] | 25 | 0 | 0 | happening
131 | [6 empty] | 4 | -4 | [6 empty] | 0 | 0 | 0
132
133 | Minor Threats
134 | A: GOVERNANCE AND MANAGEMENT OF SEG
135 | Governance
136 | Insufficient expertise, availability or independence of governing body | 1 | 4 | 1 | 2 | 1 | 9 | -5 | [6 empty] | 4 | 8 | 8
137 | Lack of 'horizon-scanning' (systematic examination of emerging issues) | 1 | 4 | 1 | 2 | 1 | 9 | -5 | [6 empty] | 4 | 8 | 8
138 | Insufficient commonality of purpose | 1 | 4 | 1 | 2 | 1 | 9 | -5 | [6 empty] | 4 | 8 | 8
139 | Lack of clear role, function or holistic strategy | 4 | 4 | 4 | 4 | 0 | 1 | 15 | [6 empty] | 16 | 256 | 0
140 | Insufficient awareness of climate change | 4 | 4 | 4 | 0 | 5 | 25 | -9 | [6 empty] | 16 | 0 | 0
141 | Lack of trust within the organisation (information not shared, access to analysis restricted) | 2 | 4 | 4 | 3 | 0 | 4 | 4 | [6 empty] | 8 | 96 | 0
142 | Prioritising USP and principles over aggregate benefits to target beneficiaries | [5 empty] | 25 | -25 | [6 empty] | 0 | 0 | 0
143 | Insufficient representation of workers and small-scale producers in governance | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
144 | Decision making
145 | Inconclusive decision-making | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
146 | Over-complex management structure | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
147 | One stakeholder group has undue influence or control over parts of the system | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
148 | ‘Universal Veto’ effectively held by one or more stakeholders or groups | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
149 | Business model
150 | Standard inadequately covers issues considered important by stakeholders | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
151 | Standard inadequately covers issues required by legislation | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
152 | Mismatch of resource allocation/resource need | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
153 | Over-emphasis on standards and certification | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
154 | Change management
155 | Limited grasp of new technology | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
156 | Lack of innovation | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
157 | Belief that the present model is the best and always will work well | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
158 | Tendency to ‘campaign and direct’ rather than ‘listen and respond’ | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
159 | Insufficient ability to influence the sustainability agenda | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
160 | Human resources
161 | Insufficient HR strategy or planning | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
162 | Insufficient staff benefits to attract or retain necessary expertise and experience | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
163 | Inadequate expertise and engagement of Board | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
164 | Insufficient training for ‘incident management’ | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
165 | Staff feel unable to suggest perceived threats | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
166 | Information and learning
167 | Insufficient data policy and management plan | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
168 | Paralysis by analysis | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
169 | B: POLITICAL AND CULTURAL
170 | Difficulties in working in priority locations | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
171 | Diversity of location-specific and product-specific issues for producers and workers | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
172 | Shifting responsibility to producers before they have sufficient resources and expertise | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
173
174 | IT and business systems misaligned | 2 | 4 | 2 | 2 | 1 | 9 | -1 | [6 empty] | 8 | 32 | 32
175 | D: ASSURANCE SYSTEM
176 | Standard and assurance system design, insufficiently facilitates certification integrity
177 | Standard system design
178 | Important issues require numerous audits over a period of time to audit effectively | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
179 | Standard too complicated to audit effectively | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
180 | Lack of prioritisation within standard | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
181 | Certification based more on conformance than performance | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
182 | Standard is more process-based than outcome- or performance-based | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
183 | Frequency of change of standard, without sufficient prior assurance impact analysis | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
184 | Standard insufficiently localised in content to facilitate credible auditing | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
185 | Excessive differences between national standards | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
186 | Assurance system design
187 | Insufficient frequency of main audits and/or surveillance audits | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
188 | Assurance non-conformity (NC) implications too lenient | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
189 | Over-reliance on remotely-acquired audit information | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
190 | “Conventional” auditing overtaken by/perceived as less credible than data systems | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
191 | Diversity of production systems makes consistent and equitable auditing difficult | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
192 | Difficulty in making changes
193 | Risk-aversion and over-confidence that present systems are sufficient | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
194 | Structural constraints to adaptation and change. (e.g. poor internal communication, dispersed multi-layered decision making) | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
195 | Quality not incentivised
196 | Insufficient connection between quality of certification and market benefit | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
197 | Auditor disincentives to raising NCs | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
198 | Inconsistent CAB approval quality
199 | CAB approval assessments too brief | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
200 | Inadequate 2-way communication and transparency
201 | Communications
202 | Limited opportunity for auditors to provide feedback on issues of concern | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
203 | Gap between what end users expect and what SEG assurance is capable of | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
204 | Difficulty for local stakeholders to submit information and concerns, including insufficient engagement by CABs | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
205 | Complaints management poorly understood by stakeholders (especially workers) and not user-friendly | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
206 | Complaints management too slow | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
207 | Insufficient response to public criticism and negative perceptions of certification integrity | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
208 | Inadequate SEG communications with CABs | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
209 | Slow response to requests for interpretations and support | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
210 | High staff turnover and lack of practical experience | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
211 | Transparency
212 | Difficulty for interested parties to understand system and find information | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
213 | Standard interpretations insufficiently transparent | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
214 | Insufficient transparency of CAB approval | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
215 | Integration
216 | Complaint and dispute resolution system not integrated across SEG, CABs and CHs | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
217 | Weaknesses in CAB-SEG-CH dynamics | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
218 | Lack of co-ordination with development of assurance in other standard systems | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
219 | Overall assurance integrity insufficient to deliver desired level of certification credibility for influential stakeholders | 2 | 3 | 2 | 1 | 3 | 16 | -10 | [6 empty] | 6 | 12 | 36
220 | E: MARKET CONDITIONS
221 | Standard insufficient to achieve objectives or differentiate in the market. | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
222 | Multiple certification costs for producers, processors or traders using multiple standards. | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
223 | Benefits to producers not sufficient to offset costs | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
224 | Benefits tied to low or unpredictable sales, or unpredictable harvests | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
225 | Demand for certified products greatly exceeding supply | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
226 | Marginal benefits of achieving and maintaining certification vary with scale of operation | 1 | 1 | 1 | 3 | 2 | 4 | -3 | [6 empty] | 1 | 3 | 6
227 | F: REPUTATION AND INFLUENCE
228 | Reduced trust associated with misunderstanding of proper certification, i.e. reporting is largely inaccurate | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
229 | Inadequate communication of impact, creating perception that organisation does not deliver value-for-money | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
230 | Overclaiming by SEG | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
231 | Inability to communicate differentiators of USP | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
232 | Perceived dilution of principles in achieving scale | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
233 | Perceptions related to 'selling out' to big business | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
234 | Allegations of corruption by staff/consultants | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
235 | Competition from more efficient NGOs | 0 | 3 | 3 | 1 | 1 | 16 | -16 | [6 empty] | 0 | 0 | 0
236 | Competition with corporate sector | 1 | 3 | 3 | 1 | 1 | 16 | -13 | [6 empty] | 3 | 9 | 9
237 | G: THREATS AT LOCAL LEVEL
238 | Local inability to raise performance to necessary level for certification
239 | Limited access to credit for certificate holders | 4 | 4 | 1 | 2 | 1 | 9 | 7 | [6 empty] | 16 | 32 | 32
240 | Multiple and changing local fishing systems | 4 | 4 | 1 | 2 | 1 | 9 | 7 | [6 empty] | 16 | 32 | 32
241 | Property rights limitations and/or violations | 4 | 4 | 1 | 2 | 1 | 9 | 7 | [6 empty] | 16 | 32 | 32
Major Threats

## Assurance Risks
| SEG Assurance Risk Management Plan | [5 empty] | Dated: | 2024-10-02 | Changes |  | Coding: 0 to 5, where 0=ok, and 5=bad. Note that 0 (not 1) is so ok, that nothing else matters anymore.
A. Likelihood, ranging from 0=absolutely impossible to 5=absolutely certain.
| Notes on process and the rational in the plan: | [9 empty] | B. Impact if it happens. From 0=no effect whatsoever, to 5=catastrophic effect.
| 1. All Assurance Threats transcribed and considered | [9 empty] | C. Options we have. From 0=we cannot do anything, to 5=it is fully in our hands.
| 2. A Likelhood and B Impact are rated 0 - 5, nil to very high | [9 empty] | D. Focus. From 0= we do not care at all, to 5=deepest concern, full in focus.
| 3. E Unmitigated risk is A x B | [9 empty] | E. Unmitigated risk = L x I
4. Target Risk in all cases is a score of 4 (low)
5. Gap = e. minus F. Colour coding indicates scale of unmitigated risk (Green - Low, Red - High)
6. Actions put into place where Gap = at least Medium to High (score of 8+)
7. Current postion described - mitigations in place
8. Mitigated risk scored and gap indicated - shows where there is still cause for concern, or further action needed or not yet taken
0 |  | A. Likelihood | B. Impact | C. Options available | D. Focus, priority | E. Unmitigated risk | F. target risk, acceptance | Gap | Actions | Position | Mitigated L | Mitigated I | Mitigated Risk at 21/11/23 | Mitigateed Gap at 21/11/23 | A*B. Raw risk | A*B*C*D. Priority | A*B*C*D*E. Alarming | Comment
55 |  | D: ASSURANCE SYSTEM
56 |  | Auditor performance, competence and skills inadequate
57 | Insufficient approved CABs | 4 | 4 | 2 | 4 | 16 | 4 | 12 | 1. Find and appoint additional CAB. 2. SEG to act as CB as a contingency. | 1. New CAB just appointed, to seek another. 2. SEG is contingency CB | 3 | 3 | 9 | 5 | 16 | 128 | 2048 | And we deal with it.
57A | SEG Panel not competent to act as CB as a contingency | 3 | 4 |  |  | 12 | 4 | 8 | 1. Design CB assurance process based on existing and previous. 2. Design andimplemene training for Panel | 1. To be done. 2. To be done | 2 | 3 | 6 | 2
58 | Auditors too lenient (Including NCs not raised, ‘low graded’ and closed too readily) including through overfamiliarity. | 2 | 3 | 2 | 2 | 6 | 4 | 2 | 1. Apply training for all new auditors. 2. Apply QA of 10% of audits | 1. All new auditors have training. 2. So far 100% of audits have been checked | 1 | 2 | 2 | -2 | 6 | 24 | 144 | All the same
59 | Auditor competence insufficient | 2 | 3 | 2 | 2 | 6 | 4 | 2 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 6 | 24 | 144
60 | Inadequate auditor training | 3 | 3 | 2 | 2 | 9 | 4 | 5 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 9 | 36 | 324
61 | Auditor qualifications, skills and experience insufficient | 2 | 4 | 2 | 2 | 8 | 4 | 4 | 1. Require qualified auditors. 2. Apply training for all new auditors and refreshers when changes | 1. Qualified auditors required. 2. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 8 | 32 | 256
62 | Audits too brief | 3 | 3 | 2 | 2 | 9 | 4 | 5 | 1. Guidance in auditor training | 1. Refresher training applied every 2 years | 1 | 2 | 2 | -2 | 9 | 36 | 324
63 | Auditors given insufficient direction with lack of consistency of findings | 2 | 4 | 2 | 2 | 8 | 4 | 4 | [6 empty] | 8 | 32 | 256
64 | Insufficient local stakeholder engagement by CABs | 2 | 4 | 2 | 2 | 8 | 4 | 4 | [6 empty] | 8 | 32 | 256
65 |  | Standard and assurance system design, insufficiently facilitates certification integrity
66 |  | Standard system design
67 | Important issues hard to detect | 4 | 4 | 1 | 1 | 4 | 4 | 12 | 1. Update Standard to include Risk Assessment, with Guidance. 2. Include in Auditor training | 1. Standard updated. 2. Included in training package | 2 | 2 | 4 | 0 | 16 | 16 | 64
68 | Indicators too open to interpretation (NB allowing CABs to interpret leniently/inconsistently) | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36 | All realistic, and we dealt with it.
69 | Standard interpretations insufficiently objective | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36
70 | Auditors over-dependent on information provided by certificate holders or applicants (CHs) | 3 | 3 | 1 | 1 | 4 | 4 | 5 | [6 empty] | 9 | 9 | 36 | Never change a winning culture
71 | Assurance system unable to adequately respond to significant growth in number of CHs | 2 | 3 | 1 | 1 | 4 | 4 | 2 | [6 empty] | 6 | 6 | 24 | The A culture should not strangle the existing creativity.
72 |  | Assurance system design
73 | Insufficient unannounced audits | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Build resource into CAB agreeement | 1. In CAB agreement | 2 | 3 | 6 | 2 | 12 | 24 | 72
74 | Insufficient sample sizes within audits | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
75 | Requiring CABs to make frequent communications with CHs about changes to the standard | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
76 | Fraud and corruption by CHs | 4 | 5 | 2 | 1 | 3 | 4 | 16 | 1. Training to auditors and CAB what to look for 2. Sufficient sanctions and control measures in Assurance System | 1. Training package updated - particularly by Lead Auditor on this topic. 2. Assurance has strong sanctions, eg. suspension | 3 | 3 | 9 | 5 | 20 | 40 | 120
77 | ‘Empty certificates’, i.e. those granted to CHs not actively engaged in harvest, production or trade | 2 | 2 | 2 | 1 | 3 | 4 | 0 | [6 empty] | 4 | 8 | 24
78 | Poor follow-up to low assurance quality | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Training for auditors to reduce low assurance quality. 2. Requirement for CAB to follow up | 1. Training package in place and refreshers due Dec 2023 2. CAB agreement in place from 7-11-23 | 2 | 2 | 4 | 0 | 12 | 24 | 72
79 |  | Oversight system design
80 | Oversight too lenient (Including NCs not raised, ‘low graded’ and closed too readily) including through overfamiliarity. | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
81 | Oversight personnel competence, training, qualifications, skills or experience insufficient | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
82 | Important issues hard to detect | 4 | 4 | 2 | 1 | 3 | 4 | 12 | 1. Training for auditors to reduce low assurance quality. 2. Requirement for CAB to follow up | 1. Training package in place and refreshers due Dec 2023 2. CAB agreement in place from 7-11-23 | 2 | 2 | 4 | 0 | 16 | 32 | 96
83 | Oversight over-dependent on information provided by CABs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
84 | CAB approval based more on conformance than performance | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
85 | Oversight system unable to adequately respond to significant growth in number of CABs | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
86 | CAB non-conformity (NC) implications too lenient | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Build performance measurew and sanctions into CAB agreement | 1. Performance measures and sanctions built into CAB agreement | 2 | 3 | 6 | 2 | 12 | 24 | 72
87 | Insufficient sample sizes within oversight | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
88 | Insufficient witness and compliance audits | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
89 | Fraud and corruption by CABs | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
90 |  | Standard-assurance interaction
91 | Inadequate risk basis to certification or CAB approval | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Update Standard to include Risk Assessment, with Guidance. 2. Include in Auditor training | 1. Standard updated. 2. Included in training package | 2 | 3 | 6 | 2 | 12 | 24 | 72
92 | Over-reliance on audits | 3 | 2 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
93 | Mixed messages and guidance on standard interpretation to CABs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
94 |  | Difficulty in making changes
95 |  | Insufficient impartiality
96 | CAB impartiality compromised by business benefits from ‘good CH relationships’ | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
97 | Auditor impartiality compromised by benefits from ‘good CH relationships’ | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Require oversight by CAB 2. Update standard and add risk assessment | 1. Oversight in CAB agreement 2. Standard updated with risk assessment and guidance | 2 | 3 | 6 | 2 | 12 | 24 | 72
98 | CABs become “Too big to fail” | 2 | 4 | 2 | 1 | 3 | 4 | 4 | [6 empty] | 8 | 16 | 48
99 |  | Quality not incentivised
100 | CABs compete more on cost than on quality; CABs incentivised to maintain and increase income from CHs | 3 | 3 | 2 | 1 | 3 | 4 | 5 | [6 empty] | 9 | 18 | 54
101 | Insufficient connection between assurance and market benefit | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
102 |  | Inconsistent CAB approval quality
103 | CAB approval assessments not frequent enough | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
104 | CAB approval inconsistent (CAB approval body not providing a level playing field for CABs) and/or too lenient | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36
105 | Insufficient competition between CAB approval bodies or insufficient control over monopolistic behaviour | 1 | 3 | 2 | 1 | 3 | 4 | -1 | [6 empty] | 3 | 6 | 18
106 | CAB approval body staff with insufficient availability and technical understanding | 3 | 4 | 2 | 1 | 3 | 4 | 8 | 1. Undertake succession planning and/or sharing of expertise | 1. To be done | 3 | 4 | 12 | 8 | 12 | 24 | 72
107 | Insufficient calibration between CABs | 2 | 3 | 2 | 1 | 3 | 4 | 2 | [6 empty] | 6 | 12 | 36